## Dashboard
Machine Load Plan
Pre-production machine loading aid with dated actions, rescheduling exceptions, and machine history consistency checks.
Operational aid only. It does not replace an ERP, MRP, MES, connected machine system, official record, certification, audit, safety, engineering, legal, tax, or compliance process.
Dated Action Plan Rows |  |  | Exceptions Requiring Rescheduling |  |  | History Sequence Exceptions |  |  | Latest Asset Records
Dated Action Plan
Completed load-plan rows are shown in planned start-date order. Replace or remove the sample rows before operational use.
Planned Start Date | Plan Item ID | Machine Identifier | Equipment ID | Reporting Period | Planned Action | Owner or Responsible Role | Required Date | Planned End Date | Required Load Hours (hours) | Available Resources (hours) | Machine/Period Planned Load Hours (hours) | Action Status | Action Sort Position
Due or Exception List — Exceptions Requiring Rescheduling
Only load-plan rows marked Reschedule Required appear here. Review the stated check results and reschedule outside this workbook as needed.
Planned Start Date | Plan Item ID | Machine Identifier | Equipment ID | Planned Action | Owner or Responsible Role | Required Date | Planned End Date | Capacity or Due-Date Check | Due or Threshold Check | Date Sequencing Check | Action Status | Exception Sort Position
Asset-Level Maintenance View
This view shows the latest recorded event for each machine and equipment combination. Event dates or readings are displayed as entered and are not interpreted or converted.
Machine Identifier | Equipment ID | Latest Event Date | Latest Reading | Owner or Responsible Role | Latest Record Status | Asset History Status | Latest Asset Sort Position

## Load Plan
Plan Item ID | Machine Identifier | Equipment ID | Reporting Period | Required Date | Planned Start Date | Planned End Date | Required Load Hours (hours) | Available Resources (hours) | Owner or Responsible Role | Planned Action | Machine/Period Planned Load Hours (hours) | Capacity or Due-Date Checks — Capacity Check | Due or Threshold Checks — Due-Date Check | Date Sequencing Check | Action Status | Action Sort Key | Example data only: rows 2-9 are examples. Replace or delete before operational use.
LP-001 | M-100 | EQ-100 | October 2026 | 2026-10-05 | 2026-10-02 | 2026-10-03 | 8 | 12 | Production Planner | Review machine load
LP-002 | M-101 | EQ-101 | October 2026 | 2026-10-06 | 2026-10-04 | 2026-10-05 | 14 | 12 | Shop-Floor Supervisor | Review machine load
LP-003 | M-102 | EQ-102 | October 2026 | 2026-10-04 | 2026-10-03 | 2026-10-05 | 6 | 8 | Production Planner | Review required date
LP-004 | M-103 | EQ-103 | October 2026 | 2026-10-09 | 2026-10-08 | 2026-10-07 | 4 | 8 | Shop-Floor Supervisor | Correct planned dates
LP-005 | M-104 | EQ-104 | October 2026 | 2026-10-08 | 2026-10-06 | 2026-10-06 | 5 | 10 | Materials Team | Review machine load
LP-006 | M-104 | EQ-104 | October 2026 | 2026-10-10 | 2026-10-07 | 2026-10-08 | 7 | 10 | Materials Team | Review machine load
LP-007 | M-105 | EQ-105 | October 2026 | 2026-10-12 | 2026-10-10 | 2026-10-11 | 6 | 8 | Production Planner | Confirm planned load
LP-008 | M-106 | EQ-106 | October 2026 | 2026-10-14 | 2026-10-12 | 2026-10-13 | 4 | 8 | Quality Coordinator | Confirm planned load

## Machine History
Machine Identifier | Equipment ID | Event Dates or Readings — Event Date (m/d/Y) | Readings (as recorded) | Owner or Responsible Role | Prior Recorded Event Date | History Consistency Check | Latest Asset Record | Latest Asset Sort Key | Event Dates or Readings. Example data only: rows 2-9 are examples. Replace or delete before operational use.
M-100 | EQ-100 | 2026-09-15 | Sample Reading 1 | Maintenance Coordinator
M-101 | EQ-101 | 2026-09-16 | Sample Reading 2 | Maintenance Coordinator
M-102 | EQ-102 | 2026-09-17 | Sample Reading 3 | Maintenance Coordinator
M-103 | EQ-103 | 2026-09-20 | Sample Reading 4 | Maintenance Coordinator
M-103 | EQ-103 | 2026-09-18 | Sample Reading 5 | Maintenance Coordinator
M-104 | EQ-104 | 2026-09-10 | Sample Reading 6 | Maintenance Coordinator
M-104 | EQ-104 | 2026-09-30 | Sample Reading 7 | Maintenance Coordinator
M-105 | EQ-105 | 2026-09-25 | Sample Reading 8 | Maintenance Coordinator

## Instructions
Machine Load Plan Instructions
Use this workbook before production release to organize machine loading entries, check date sequencing, capacity or due-date checks, due or threshold checks, and review entered machine history consistency.
1. Start with the Load Plan sheet
Enter one machine loading item per row. Use a Plan Item ID, Machine Identifier, Equipment ID, Reporting Period, Required Date, Planned Start Date, Planned End Date, Required Load Hours, Available Resources, Owner or Responsible Role, and Planned Action. Enter dates as Excel dates displayed in m/d/Y format. Enter load and available resource values as hours. This workbook does not convert units. Use the same Machine Identifier and Reporting Period spelling for related rows so the machine-and-period planned load calculation can group them correctly. Enter available resources consistently for rows that represent the same machine and reporting period. Replace or delete the example sample rows before operational use.
2. Review date sequencing and capacity or due-date checks
Machine/Period Planned Load Hours: Total required load hours for the matching Machine Identifier and Reporting Period. Capacity or Due-Date Checks: Capacity Exception appears when total planned load hours are greater than entered available resources. Due or Threshold Checks: Due-Date Exception appears when Planned End Date is later than Required Date. Date Sequencing Check: Date Sequence Exception appears when Planned End Date is earlier than Planned Start Date. Action Status: Reschedule Required appears when any of the three checks shows an exception. Planned appears when the three checks are acceptable.
3. Use the Dashboard outputs
Review the summary metrics first. Use the Dated Action Plan as the date-ordered view of completed load-plan rows. Use the Due or Exception List for exceptions requiring rescheduling. Review the stated check results before changing dates, hours, or responsible roles. The workbook identifies exceptions only. It does not choose a replacement date, a replacement machine, or a revised available-resources amount.
4. Enter event dates or readings in Machine History
Enter machine and equipment identifiers, event dates or readings, and the owner or responsible role. Use the Event Date field for Excel dates displayed in m/d/Y format and use the Readings field for readings as recorded. Readings are displayed as entered and are not interpreted or converted. Enter events in the intended record sequence for each machine and equipment combination. A History Sequence Exception indicates an event date that is not later than the prior entered event date for the same machine and equipment combination. The Dashboard asset-level maintenance view shows the latest entered event-date record for each machine and equipment combination.
5. Boundaries and limitations
This workbook is an operational planning aid. It does not replace an ERP, MRP, MES, connected machine system, official record, certification, audit, safety process, engineering review, legal review, tax process, quality approval, or regulatory compliance process. It does not calculate maintenance intervals, production resource gaps, machine rates, or rescheduling decisions.
6. Workbook maintenance
The Load Plan and Machine History sheets each contain 100 prepared rows. Add entries only within the prepared range unless the workbook structure, formulas, validation, formatting, and dashboard extraction ranges are intentionally extended together. Do not overwrite pale blue or light gray formula cells. Keep input cells in the pale yellow areas. Review formula results after entering or changing input values.