## Dashboard
Production Schedule
Plan open work orders before production release using entered due dates, routing hours, and resource calendars.
Schedule Summary |  |  | Planner Review
Open Work Orders |  |  | Review resource loading by date, the multi-day schedule, and rescheduling exceptions before production release.
Work Orders With Rescheduling Exceptions |  |  | This workbook does not release work orders or move work automatically.
Work Orders Marked Late Risk |  |  | Sample data is illustrative only. Replace it with current planning information before use.
Ready Schedule Allocations
Schedule Allocation Exceptions
Multi-Day Resource Schedule | [6 empty] | Rescheduling Exception List
Planned Date | Resource | Work Order ID | Planned Routing Hours | Due Date | Available Routing Hours | Resource-Date Scheduled Routing Hours | Exception Source | Work Order ID | Rescheduling Exception | Related Date | Related Routing Hours

## Work Orders
Open Work Orders
Enter each open work order, its due date, and total routing hours. Sample rows are illustrative only and must be replaced.
Work Order ID | Due Date | Routing Hours | Total Planned Routing Hours | Remaining Routing Hours | Latest Planned Date | Late-Order Risk | Rescheduling Exception | Exception Sequence
Sample Work Order 1001 | 2026-09-08 | 4
Sample Work Order 1002 | 2026-09-09 | 6
Sample Work Order 1003 | 2026-09-09 | 8
Sample Work Order 1004 | 2026-09-10 | 3
Sample Work Order 1005 | 2026-09-10 | 5
Sample Work Order 1006 | 2026-09-11 | 4
Sample Work Order 1007 | 2026-09-11 | 6
Sample Work Order 1008 | 2026-09-10 | 2

## Resource Schedule
Resource Calendar and Multi-Day Schedule
Enter resource calendar availability first. Then assign planned routing hours by date, resource, and work order. Sample rows are illustrative only and must be replaced.
Calendar Date | Resource | Available Routing Hours | Resource Loading by Date (Scheduled Routing Hours) | Remaining Routing Hours | Calendar Status | Planned Date | Resource | Work Order ID | Planned Routing Hours | Due Date | Work Order Routing Hours | Total Planned Routing Hours | Remaining Routing Hours | Available Routing Hours | Resource-Date Scheduled Routing Hours | Schedule Check | Exception Sequence | Ready Schedule Sequence
2026-09-08 | Sample Resource A | 8 |  |  |  | 2026-09-08 | Sample Resource A | Sample Work Order 1001 | 4
2026-09-08 | Sample Resource B | 6 |  |  |  | 2026-09-08 | Sample Resource B | Sample Work Order 1002 | 6
2026-09-09 | Sample Resource A | 8 |  |  |  | 2026-09-09 | Sample Resource A | Sample Work Order 1003 | 8
2026-09-09 | Sample Resource B | 6 |  |  |  | 2026-09-09 | Sample Resource B | Sample Work Order 1004 | 3
2026-09-10 | Sample Resource A | 8 |  |  |  | 2026-09-10 | Sample Resource A | Sample Work Order 1005 | 5
2026-09-10 | Sample Resource B | 6 |  |  |  | 2026-09-10 | Sample Resource B | Sample Work Order 1006 | 4
2026-09-11 | Sample Resource A | 8 |  |  |  | 2026-09-11 | Sample Resource A | Sample Work Order 1007 | 6
2026-09-11 | Sample Resource B | 6 |  |  |  | 2026-09-11 | Sample Resource B | Sample Work Order 1008 | 2

## Instructions
Production Schedule Instructions
Use this workbook to plan work orders before production release.
Step or Topic | Instructions
Step 1 — Enter Open Work Orders | Enter one work order ID, due date, and total routing hours on the Work Orders sheet. Use one unique work order ID per work order. Replace all sample rows before using the workbook for planning.
Step 2 — Enter Resource Calendar Availability | On the Resource Schedule sheet, enter one resource calendar row for each planned date and resource. Enter available routing hours for that resource-date combination. Do not enter the same date and resource combination more than once.
Step 3 — Build the Multi-Day Schedule | Enter planned date, resource, work order ID, and planned routing hours in the Multi-Day Schedule table. Enter the resource calendar row before assigning the related schedule allocation. A work order may use more than one schedule allocation row when routing hours are planned across multiple dates. Keep schedule allocation rows in planned-date order when practical.
Step 4 — Review Resource Loading by Date | Review Resource Loading by Date, Remaining Routing Hours, and Calendar Status in the Resource Calendar. Calendar Status shows whether the entered schedule fits the entered available routing hours. Resolve Overloaded and Duplicate Calendar Entry results before production release planning.
Step 5 — Review Work Order Risk | Unscheduled Hours means planned routing hours are below the work order routing hours. Overallocated means planned routing hours exceed the work order routing hours. Late means the latest planned date is after the due date. On Schedule means routing hours are fully planned and the latest planned date is on or before the due date.
Step 6 — Review the Dashboard | The Multi-Day Resource Schedule shows allocation rows marked Ready. The Rescheduling Exception List combines work order risks and schedule allocation exceptions. Review and correct exceptions before production release planning.
Schedule Check Definitions | Work Order Missing — The entered work order ID is not listed on the Work Orders sheet. Calendar Missing — No matching resource calendar entry exists for the planned date and resource. Duplicate Calendar Entry — More than one resource calendar row exists for the same date and resource. Work Order Overallocated — Total planned routing hours exceed the work order routing hours. Resource Overloaded — Total scheduled routing hours exceed available routing hours. Ready — The allocation has a valid work order, a valid calendar entry, does not overallocate work order routing hours, and does not overload the resource-date availability.
Workbook Boundary | This workbook is an operational planning aid for open work orders before production release. It does not release work orders, automatically dispatch work, move work between resources, confirm production completion, connect to machines, or replace an ERP, MRP, MES, or real-time production system. No external standards, authority requirements, or official sources are built into this workbook.